## Slide 1: Project Management Critical Path Method

## Slide 26: Example 2
Develop the network for a project with following activities and immediate predecessors:
Activity Immediate
predecessors
A -
B -
C B
D A, C
E C
F C
G D,E,F
Try to do for the first five (A,B,C,D,E) activities

## Slide 27: Network of first five activities
1
3
4
2
A
B
C
D
5
E
We need to introduce a dummy activity

## Slide 28
Note how the network correctly identifies D, E, and F as the immediate predecessors for activity G.
Dummy activities is used to identify precedence relationships correctly and to eliminate possible confusion of two or more activities having the same starting and ending nodes
Dummy activities have no resources (time, labor, machinery, etc) – purpose is to PRESERVE LOGIC of the network
Network of Seven Activities
1
3
4
2
A
B
C
D
5
E
7
6
F
G
dummy

## Slide 29
EXAMPLES OF THE USE OF DUMMYACTIVITY
Dummy
RIGHT 
1
1
2
Activity c not required for e
a
b
c
d
e
a
b
c
d
e
WRONG!!!
RIGHT 
Network concurrent activities
1
2
1
2
3
a
WRONG!!!
a
b
b
WRONG !
RIGHT 

## Slide 30
1
1
2
2
3
3
4
a
d
b
e
c
f
a
d
b
e
f
c
WRONG!!!
RIGHT!!!
a precedes d.
a and b precede e,
b and c precede f (a does not precede f)

## Slide 31: Scheduling with activity time
Activity Immediate Completion
predecessors Time (week)
A - 5
B - 6
C A 4
D A 3
E A 1
F E 4
G D,F 14
H B,C 12
I G,H 2
Total …… 51
This information indicates that the total time required to complete activities is 51 weeks. However, we can see from the network that several of the activities can be conducted simultaneously (A and B, for example).

## Slide 32: Arc with ES & EF time
1
2
A [0,5]
5
Activity
ES = earliest start time
EF = earliest finish time
t = expected activity
time

## Slide 33: Network with ES & EF time
1
3
4
2
5
7
6
A[0,5]
5
B[0,6]
6
C[5,9]
4
D[5,8]
3
E[5,6]
1
F[6,10]
4
G[10,24]
14
H[9,21]
12
I[24,26]
2
Earliest start time rule:
The earliest start time for an activity leaving a particular node is equal to the largest of the earliest finish times for all activities entering the node.

## Slide 34: Activity, duration, ES, EF, LS, LF
2
3
C [5,9]
4 [8,12]
Activity
ES = earliest start time
EF = earliest finish time
LF = latest finish time
LS = latest start time

## Slide 35: Network with LS & LF time
1
3
4
2
5
7
6
A[0,5]
5[0,5]
B[0,6]
6[6,12]
C[5,9]
4[8,12]
D[5,8]
3[7,10]
E[5,6]
1[5,6]
F[6,10]
4[6,10]
G[10,24] 14[10,24]
H[9,21]
12[12,24]
I[24,26]
2[24,26]
Latest finish time rule:
The latest finish time for an activity entering a particular node is equal to the smallest of the latest start times for all activities leaving the node.